## Slide 1: Why now: failover is slow and the platform is out of support
1 Why now · Business driver
2 The issue · Current risk
3 The measures · KPIs
4 The plan · Remediation
5 The timeline · Roadmap
Failover
Slow recovery
During patching and DCR, leader election and under-replicated partition recovery run long on the 2.5-DC stretch cluster. PROD reports this frequently.
2.8.1
Unsupported Kafka
End of life since Sep 2022; Apache is on 4.3. Kafka 4.x drops ZooKeeper, so the path runs via 3.9 (KRaft) on Java 17.
CVEs
Security exposure
Known flaws in 2.8.1 include CVE-2022-34917 (broker DoS) and CVE-2025-27819 (JAAS RCE), both CVSS 7.5.
RHEL 7
Unsupported OS
About 28 VMs (14 in PROD) at the start, some since migrated. Red Hat maintenance ended 30 Jun 2024.
Why the audit comes first: excess partitions are what slow failover today, and every topic we retire is one we do not have to upgrade, secure or migrate to BSP 2.0.
Notes: WHY NOW – the purpose of doing this here and now. - Operational (lead reason): EMEA runs a 2.5-DC stretch cluster. During patching cycles and DCR activity, failover/failback is slow: leader election takes much longer and under-replicated partition (URP) recovery is extended because partition counts are far above recommended levels. The PROD team has confirmed this happens very frequently. - Kafka 2.8 released Apr 2021; last patch 2.8.2 Sep 2022; end of life. We run 2.8.1, so we lack even the 2.8.2 fix for CVE-2022-34917. Apache Kafka is on 4.3 (4.3.2 current). - Kafka 4.x is KRaft-only: ZooKeeper clusters must migrate to KRaft first (3.9 is the bridge). 4.x brokers need Java 17; clients need 2.1+ and Java 11+. - CVEs on 2.8.1 (examples): CVE-2022-34917 broker memory DoS (7.5, fixed 2.8.2); CVE-2025-27819 JndiLoginModule RCE/DoS, 2.0.0–3.3.2 (7.5); CVE-2024-31141 ConfigProvider file read (fixed 3.8.0); CVE-2023-25194 Kafka Connect JNDI (Connect REST on 8083 is in use). - RHEL 7: ~28 VMs across PROD and UAT at the start of the exercise (~14 PROD); some already migrated; further analysis under way may adjust the count. Maintenance ended 30 Jun 2024; ELS for 7.9 to 31 May 2029 (paid). Sources: kafka.apache.org/43/getting-started/upgrade; endoflife.ai/apache-kafka/2.8; Broadcom advisory 36810; cve.org CVE-2025-27819; redhat.com RHEL 7 end-of-maintenance.

## Slide 2: The issue: partitions and memory are the constraint
1 Why now · Business driver
2 The issue · Current risk
3 The measures · KPIs
4 The plan · Remediation
5 The timeline · Roadmap
226K
PROD partitions
≈4.5K per broker on 50 brokers
694K
UAT partitions
≈13.9K per broker – 3.5× guidance
90%
JVM heap, busiest brokers
60–90% across PROD brokers
Not the constraint
Storage ≈60%. CPU ≈20%, peaks 40–50%.
EMEA partitions per broker vs ZooKeeper-mode guidance
Chart: 
| Guidance (max) | PROD today | UAT today
Partitions per broker | 4000 | 4520 | 13880
≈ +2K / week
Grafana: ≈216K (15 Oct) → ≈220K (30 Oct)
≈270 / day
Net new PROD partitions, every day
+20K
More PROD partitions in 10 weeks if unchecked
Guidance: ≤4,000 partitions per broker, ≤200,000 per cluster.
What we cannot see today
Topic-to-system-ID mapping, which blocks per-system network quotas
Which topics and partitions are dormant
How much of the JVM heap the partition count drives
Notes: THE ISSUE – EMEA BSP v1 (50 brokers PROD, 50 UAT, Kafka 2.8.1, ZooKeeper, 2.5-DC stretch). - PROD 226K partitions (~4,520 per broker). UAT 694K (~13,880 per broker). Assumes counts include replicas, as the guidance does. - Guidance (Confluent / Apache, ZooKeeper mode): up to 4,000 partitions per broker and 200,000 per cluster. Above this, controller failover, broker restarts and leader elections slow down – exactly the failover/failback symptom PROD sees during patching and DCR. - Topic ownership is known, but there is no visibility of the mapping between topics and system IDs. That mapping is needed to set and enforce network (client) quotas per system ID. - Memory: Grafana shows JVM heap at 60–90% on PROD brokers, reaching 90% on the busiest, depending on load. Partition cleanup alone may not bring heap down materially – we re-measure after cleanup and then decide on vertical scaling (heap/RAM) vs horizontal scaling. - Storage ~60% and CPU ~20% average (peaks 40–50%) are not the bottleneck. Still to check: CPU spike during a broker restart cycle. - Growth velocity (PROD), from Grafana "Kafka Overview – Total PartitionCounts", EMEA PROD, last 30 days: ~216.3K on 15 Oct -> ~220.4K on 30 Oct = ~+4.1K in 15 days, i.e. ~270 per day, ~1.9K per week (~+1.9% in two weeks, ~40 per broker per week). Steady step-ups, no reductions – nothing is being cleaned up today. Linear projection: ~+20K over a 10-week audit, ~+100K in a year. Cleanup therefore has to cut today's excess AND offset ongoing growth, so topic-creation guardrails and recurring hygiene are part of the fix. - The short drops on the Grafana chart are gaps in metric collection, not real changes; they are excluded from the growth calculation. - Note: Grafana currently shows ~220K; the 226K headline comes from a separate count. Reconcile the two sources (e.g. replicas vs partitions, internal topics) before presenting. - Realistic PROD floor: if excess topics are not the main driver of partition growth, cleanup likely bottoms out around 150–160K. Target <180K.

## Slide 3: Across regions: EMEA is stretched, AMR capacity sits idle
1 Why now · Business driver
2 The issue · Current risk
3 The measures · KPIs
4 The plan · Remediation
5 The timeline · Roadmap
EMEA
Under pressure
50
PROD brokers
50
UAT brokers
Heaviest load: 226K PROD partitions
No spare VMs to add
AMR
Idle capacity
12
PROD brokers
36
UAT brokers
PROD needs expansion to match UAT
24 VMs procured for PROD, idle ~2 years
New broker requests risk the same fate
APAC
Low traffic
12
PROD brokers
28
UAT brokers
12 PROD VMs are sufficient today
PROD expansion planned, no clear benefit
Status of VM requests unconfirmed
Clean up partitions first
Attach the 24 idle VMs
Hold expansion; review requests
Principle: use the capacity we already own before buying more. Audit covers all three regions; EMEA PROD is the priority.
Notes: REGIONAL VIEW – the audit runs across EMEA, AMR and APAC; EMEA PROD is the heaviest hitter. - EMEA: 50 PROD / 50 UAT brokers. Nothing spare for PROD. The RHEL 7 brokers once considered for repurposing (to reach 52) turned out to be GL VMs that must be fully decommissioned, so they are not an option. - AMR: PROD has 12 brokers; UAT was expanded to 36. A matching PROD expansion (+24 VMs to reach 36) was requested and the VMs were provisioned, but they have not been attached to the cluster for about two years. Cause unclear (bandwidth or prioritisation with the RTP team). Attaching them is the fastest capacity gain and avoids new spend. New broker requests for the current expansion risk sitting idle in the same way. - APAC: 12 PROD brokers, minimal traffic – sufficient. UAT expanded to 28 for an expected use case that has not materialised. A similar PROD expansion is planned but no benefit is visible. Procurement requests from that time had availability issues; need to confirm whether they were fulfilled, partially fulfilled or are still open. - Node counts are from the working session; confirm against CMDB before presenting.

## Slide 4: The measures: nine KPIs, baselined now and tracked to target
1 Why now · Business driver
2 The issue · Current risk
3 The measures · KPIs
4 The plan · Remediation
5 The timeline · Roadmap
Area | Measure | Current | Target | Why it matters
Partitions – PROD | Total (per broker) | 226K (4.5K) | <180K (<3.6K) | Faster failover and failback
Partition growth | Net new PROD partitions per week | ≈ +2K | Approved only | Stops the estate drifting back
Partitions – UAT | Total (per broker) | 694K (13.9K) | ≤200K (≤4K) | Remove test sprawl; stable UAT
Failover | Leader election and URP recovery time | Slow – baseline | Agreed SLA | Safe patching and DCR
Memory | JVM heap, busiest brokers | 60–90% | Re-measure | Decides vertical vs horizontal scaling
Storage / CPU | Disk used; CPU average (peak) | 60%; 20% (50%) | Hold ≤70% | Headroom stays intact
Idle capacity | Procured VMs not in service (AMR) | 24 | 0 | Use what we own before buying
System-ID mapping | Topics mapped to a system ID | No visibility | 100% | Per-system network quotas
Unsupported OS | RHEL 7 VMs (PROD + UAT) | ≈28 | 0 | Closes audit finding
Targets are proposed. Baselines are confirmed in Weeks 1–3 and reported on a weekly management scorecard.
Notes: THE MEASURES – current vs target. - PROD partitions 226K -> <180K (~20% cut). Realistic floor 150–160K if excess topics are not the main driver. <180K = <3,600 per broker, under the 4,000 guidance. - Partition growth: Grafana shows PROD ~216K (15 Oct) -> ~220K (30 Oct), ~1.9K/week net, ~270/day. Target = only approved growth, enforced by topic-creation guardrails and per-system quotas. - UAT 694K -> <=200K proposed: UAT has the largest reduction opportunity and is the safest place to start. - Failover: measure leader-election duration and time to zero under-replicated partitions after a broker restart, during the next patching cycle. Agree an SLA with the PROD team once the baseline is known. - System-ID mapping: owners are known, but topic-to-system-ID mapping is not visible; 100% mapping enables network quotas per system ID and supports BSP 2.0 sizing. - Memory: JVM heap 60–90% today (90% on the busiest brokers). After cleanup, rerun the JVM analysis; then decide whether to increase heap/RAM (vertical) or add brokers (horizontal). Cleanup alone may not lower heap much – that is why this KPI's target is a decision, not a number. - Storage ~60% and CPU ~20% (peaks 40–50%) are healthy; the KPI is to hold them. Also monitor a restart cycle for CPU spikes. - Idle capacity: 24 AMR PROD VMs provisioned ~2 years ago and never attached. Target zero idle – attach or release. - RHEL 7: ~28 VMs (≈14 PROD) at the start; some migrated since; count being refined by further analysis. - Supporting health signals on the scorecard: under-replicated partitions = 0 in steady state, offline partitions = 0, consumer lag within SLA.

## Slide 5: The plan: clean up first, then size on evidence, then harden
1 Why now · Business driver
2 The issue · Current risk
3 The measures · KPIs
4 The plan · Remediation
5 The timeline · Roadmap
1 Clean up
Map topics to system IDs; find dormant ones
Remove with owner sign-off, UAT first
Rebuild over-partitioned topics (counts cannot shrink in place)
Make cleanup a recurring hygiene cycle
Moves: partitions, failover, system IDs
2 Size on evidence
Rerun JVM heap analysis after cleanup
Then decide: more heap/RAM or more brokers
Measure CPU and election time on a restart
Attach AMR's 24 idle VMs before buying more
Moves: memory, idle capacity
3 Harden & prepare
Patch or formally accept open CVEs
Exit RHEL 7; decommission GL VMs
Confirm path: 2.8 → 3.9 (KRaft) → 4.x on Java 17
Map workloads for BSP 2.0 placement
Moves: security, upgrade readiness
Order matters: shrinking the partition count first tells us whether we need to scale at all – and which way.
Notes: THE FIX – three workstreams in sequence. 1 Clean up: dormant = no produce/consume activity over an agreed window, confirmed by the owner. Kafka cannot reduce a topic's partition count in place, so over-partitioned topics are recreated at the right size and tenants cut over. All deletions under change control. Make it a periodic cleanup so the estate does not drift back. 2 Size on evidence: after cleanup, rerun JVM heap/GC analysis. If heap stays at 60–90%, test vertical scaling (heap/RAM) first; if that is not enough, horizontal. Observe a broker restart cycle for CPU spikes and election time. In AMR, attach the 24 provisioned-but-idle PROD VMs before any new purchase. 3 Harden & prepare: CVE patching or config mitigations (restrict AlterConfigs, disallow JndiLoginModule, Connect client override policy); RHEL 7 exit and full decommission of the GL VMs; upgrade route 2.8 -> 3.9 (KRaft) -> 4.x, Java 17 brokers, clients >= 2.1. Kafka upgrade stays secondary to tenant migration to BSP 2.0.

## Slide 6: The timeline: 10 weeks, three gates, results reported weekly
1 Why now · Business driver
2 The issue · Current risk
3 The measures · KPIs
4 The plan · Remediation
5 The timeline · Roadmap
Weeks 1–3
1 Discovery & audit
Output: Inventory across all regions, risk register, KPI baselines
Gate 1: Inventory and findings accepted
Weeks 4–5
2 Remediation planning
Output: Prioritised cleanup plan with owners and change windows
Gate 2: Plan and KPI targets approved
Weeks 6–10+
3 Cleanup & validation
Output: UAT then PROD cleanup; JVM re-scan; scaling decision
Gate 3: Fixes verified, residual risks signed off
Decisions needed today
1
Confirm scope and topic-to-system mapping
2
Endorse targets: PROD <180K, UAT ≤200K
3
Approve change windows: UAT, then PROD
4
Get AMR's 24 idle VMs attached
Notes: THE TIMELINE – executive working proposal, Oct 2026. Audit dates and KPI targets subject to validation. - Weeks 1-3: inventory EMEA, AMR and APAC (clusters, brokers, topics, owners, idle VMs, RHEL 7 VMs); baseline all KPIs including failover timings from the next patching cycle. - Weeks 4-5: prioritise; agree owners, change windows and KPI targets. - Weeks 6-10+: cleanup UAT then PROD under change control; rerun JVM analysis; decide vertical vs horizontal scaling; attach AMR idle VMs; validate and sign off residual risks. Weekly scorecard to management.