## Slide 1
BSP V1 | KAFKA PLATFORM ASSURANCE
BSP v1 Kafka Platform | Audit roadmap
On-prem estate inventory → risk-based remediation plan → controlled execution
Executive working proposal • 29 Oct 2026 • Audit dates and KPI targets subject to validation
01
01
DISCOVERY & AUDIT
Weeks 1–3
Inventory BSP v1 on-prem Kafka clusters, owners, versions, dependencies and control gaps.
Inventory + risk register
→
02
REMEDIATION PLANNING
Weeks 4–5
Prioritize critical risks; assess impact, effort, ownership and approvals.
Sequenced action plan
→
03
REMEDIATION & VALIDATION
Weeks 6–10+
Fix approved issues, verify controls and track accepted residual risks.
Validated closures
PROPOSED DELIVERY WINDOW
W1
W2
W3
W4
W5
W6
W8
W10+
GATE 1 Inventory and findings accepted • GATE 2 Prioritized plan approved • GATE 3 Fixes verified / residual risks signed off

## Slide 2
BSP V1 | KAFKA PLATFORM ASSURANCE
Management dashboard | How success will be measured
Simple leading indicators for coverage, risk reduction, accountability and delivery
Executive working proposal • 29 Oct 2026 • Audit dates and KPI targets subject to validation
02
INVENTORY COVERAGE
100%
BSP v1 clusters mapped to owner and environment
RISK ASSESSMENT
100%
BSP v1 clusters assessed and risk-rated
CRITICAL RISK CONTROL
0 overdue
Critical findings past approved due date
ACTION OWNERSHIP
100%
High/critical findings with a named owner
MANAGEMENT DECISION POINTS
1 Confirm scope & owners
2 Approve risk-based plan
3 Accept closures / exceptions
BSP v1 audit focus: security hardening • unsupported estate / REL7 • observability gaps • tenant migration readiness • risk approvals